## Sheet1
				Date	Week	Day	MSc Project Tasks
				30th Mar	0	Sat	Read, make notes, and summarize from 2 papers
				31st Mar	0	Sun	Read, make notes, and summarize from 3 papers
				1st Apr	1	Mon
				2nd Apr	1	Tues	Read, make notes, and summarize from 2 papers
	MSc Project Tasks			3rd Apr	1	Wed	Presentation of initial background research
	Research and summarise from 7 papers for grad project	2nd April		4th Apr	1	Thurs
	Presentation of initial background research	3rd April		5th Apr	1	Fri	Print off 7 papers on CRFs/RNNs
	Find, print, and make notes from 5 papers on CRFs/RNNs			6th Apr	1	Sat	Make 2 week plan to present
	Northstar background research and note taking			7th Apr	1	Sun	Build IMU .py scripts (graph and cluster functions)
	Find, print, and make notes from 5 papers on time-series regression			8th Apr	2	Mon	Read / make notes from 1 paper
	Type up notes thus far			9th Apr	2	Tues	Read / make notes from 1 paper	Read ML textbook, 19.0 – 19.6
				10th Apr	2	Wed	Go to meeting
				11th Apr	2	Thurs
				12th Apr	2	Fri	Python: add supervised learning functionality to IMU datasets	Python: setup git repo for project
				13th Apr	2	Sat
				14th Apr	2	Sun
				15th Apr	3	Mon
Project time	Project Tasks			16th Apr	3	Tues
				17th Apr	3	Wed	Find further 5 papers relating to CRFs/RNNs and action/motion analysis	Create research papers folder and file previous papers
	Find further 5 papers relating to CRFs/RNNs and action/motion analysis	17th Apr		18th Apr	3	Thurs	Setup laptop for CUDA / TF GPU	Read and complete programs in 'Python ML', ch 16
	Create research papers folder and file previous papers	17th Apr		19th Apr	3	Fri	URL link review: “Overview of Conditional Random Fields”	URL link review: “Performing Sequence Labelling using CRF in Python”
	Setup laptop for CUDA / TF GPU	18th Apr		20th Apr	3	Sat
	Read and complete programs in 'Python ML', ch 16	18th Apr		21st Apr	3	Sun	URL link review: “Conditional Random Fields for Sequence Prediction”	URL link review: “Conditional Random Fields for Sequence Prediction”
	URL link review: “Overview of Conditional Random Fields”	19th Apr		22nd Apr	4	Mon	Make RNN / CRF presentation (2 slides each, 1 description, 1 usefulness)
	URL link review: “Performing Sequence Labelling using CRF in Python”	19th Apr		23rd Apr	4	Tues	Print and file: 'Feature learning papers', 'Medical stuff', 'RNN stuff', 'CRF stuff'	Paper review: “Conditional Random Fields for Activity Recognition in Smart Environments”
	URL link review: “Conditional Random Field Tutorial in PyTorch”	21st Apr		24th Apr	4	Wed	Paper review: “Deep, Convolutional, and Recurrent Models for HAR using Wearables”	Do RNN / CRF presentation
	URL link review: “Conditional Random Fields for Sequence Prediction”	21st Apr		25th Apr	4	Thurs	Go for 1-on-1 meeting
	Make RNN / CRF presentation (2 slides each, 1 description, 1 usefulness)	22nd Apr		26th Apr	4	Fri	Type up and make import points from: “Cond Random Fields: Prob Models for Sequencing”	Type up and make import points from: “CRFs as RNNs”	Paper review: “Action Categorization with Modified Hidden Conditional Random Field”
	Print and file: 'Feature learning papers', 'Medical stuff', 'RNN stuff', 'CRF stuff'	23rd Apr		27th Apr	4	Sat	Type up and make import points from: “CRFs for AR in Smart Environments”	Type up and make import points from: “Deep, Conv, and Recurrent Models for HAR using Wearables”
	Paper review: “Conditional Random Fields for Activity Recognition in Smart Environments”	23rd Apr		28th Apr	4	Sun	Paper review: “Deep Recurrent NN for Mobile HAR with High Throughput”	Find, print, file, and make plan for papers regarding RNNs for HAR	Paper review: “Hidden CRFs for Gesture Recognition”
	Paper review: “Deep, Convolutional, and Recurrent Models for HAR using Wearables”	24th Apr		29th Apr	5	Mon
	Do RNN / CRF presentation	24th Apr		30th Apr	5	Tues	Paper review: “Hierarchical Recurrent Neural Network for Skeleton Based Action Recognition”	Programming: Download/setup suit data and create diffs plot function
	Go for 1-on-1 meeting	25th Apr
	Type up and make import points from: “Cond Random Fields: Prob Models for Sequencing”	26th Apr		1st May	5	Wed	Paper review: “Continuous Conditional Random Fields for Regression in Remote Sensing”	Programming: add function to extract statistical features of joint files + print results to separate .csv
	Type up and make import points from: “CRFs as RNNs”	26th Apr		2nd May	5	Thurs	Type up and make import points from: “Action Categorization with Modified Hidden CRF”	Programming: create extract/dynamic visualisation functions for all-data files
	Paper review: “Action Categorization with Modified Hidden Conditional Random Field”	26th Apr		3rd May	5	Fri
	Type up and make import points from: “CRFs for AR in Smart Environments”	27th Apr		4th May	5	Sat
	Type up and make import points from: “Deep, Conv, and Recurrent Models for HAR using Wearables”	27th Apr		5th May	5	Sun
	Paper review: “Deep Recurrent NN for Mobile HAR with High Throughput”	28th Apr		6th May	6	Mon
	Find, print, file, and make plan for papers regarding RNNs for HAR	28th Apr		7th May	6	Tues
	Paper review: “Hidden CRFs for Gesture Recognition”	28th Apr		8th May	6	Wed
	Paper review: “Hierarchical Recurrent Neural Network for Skeleton Based Action Recognition”	30th Apr		9th May	6	Thurs
	Programming: Download/setup suit data and create diffs plot function	30th Apr		10th May	6	Fri
	Paper review: “Continuous Conditional Random Fields for Regression in Remote Sensing”	1st May		11th May	6	Sat
	Programming: add function to extract statistical features of joint files + print results to separate .csv	1st May		12th May	6	Sun
	Type up and make import points from: “Action Categorization with Modified Hidden CRF”	2nd May		13th May	7	Mon
	Programming: create extract/dynamic visualisation functions for all-data files	2nd May		14th May	7	Tues
				15th May	7	Wed
3rd May	Paper review: “Actionness Ranking with Lattice Conditional Ordinal Random Fields”			16th May	7	Thurs
3rd May	Paper review: “Long-term Recurrent Convolutional Networks for Visual Recognition and Description”			17th May	7	Fri
4th May	Programming: add to DC init function (inc extract table to .csv and read in, and passing to JA objects)			18th May	7	Sat
	Programming: add Fourier analysis functionality to statistical extraction for AD and JA classes (veloc+accel)			19th May	7	Sun
4th May	Paper review: “Sequential Deep Learning for Human Action Recognition”			20th May	8	Mon
4th May	Paper review: “Differential RNNs for Action Recognition”			21st May	8	Tues
5th May	Paper review: “Spatio-Temporal LSTM with Trust Gates for 3D HAR”			22nd May	8	Wed
5th May	Paper review: “Co-Occurrence Feature Learning for Skeleton Based AR using Regularized DLSTM Networks”			23rd May	8	Thurs
5th May	Type up and make import points from: “Deep Recurrent NN for Mobile HAR with High Throughput”			24th May	8	Fri
6th May	Paper review: “Online Detection and Classification of Dynamic Hand Gestures with Recurrent 3D CNNs”			25th May	8	Sat
6th May	Type up and make import points from: “Hidden CRFs for Gesture Recognition”			26th May	8	Sun
6th May	Type up and make import points from: “Hierarchical Recurrent Neural Network for Skeleton Based AR”			27th May	9	Mon
7th May	Type up and make import points from: “Continuous CRFs for Regression in Remote Sensing”			28th May	9	Tues
7th May	Type up and make import points from: “Actionness Ranking with Lattice Conditional Ordinal Random Fields”			29th May	9	Wed
7th May	Type up and make import points from: “Long-term Recurrent CNNs for Visual Recognition and Description”			30th May	9	Thurs
				31st May	9	Fri

	Paper review: “Conditional Models for Contextual Human Motion Recognition”
	Paper review: “Conditional Random People: Tracking Humans with CRFs and Grid Filters”

	Paper review: “Deep Convolutional and LSTM Recurrent NNs for Multimodal Wearable AR”

	Paper review: “HAR and Pattern Discovery”
	Paper review: “A Comprehensive Study of Activity Recognition Using Accelerometers”
	Paper review: “An Analysis of Single-Layer Networks in Unsupervised Feature Learning'
	Paper review: “Simultaneous Feature Learning and Hash Coding with Deep Neural Networks”
	Paper review: “Discriminative Unsupervised Feature Learning with CNNs”
	Write 2-3 preliminary pages of report on background research and tasks undertaken
	Type up and organize notes from papers (separate sections for CRF/RNN/feature learn, etc)
	URL link review: “Lecture 13: Variational Inference: Mean Field Approximation”
	Read and take notes from 'Sequence Modeling: Recurrent and Recursive Nets'