## Sheet1
			Date	Week	Day	MSc Project Tasks
			30th Mar	0	Sat	Read, make notes, and summarize from 2 papers
			31st Mar	0	Sun	Read, make notes, and summarize from 3 papers
			1st Apr	1	Mon
			2nd Apr	1	Tues	Read, make notes, and summarize from 2 papers
MSc Project Tasks			3rd Apr	1	Wed	Presentation of initial background research
Research and summarise from 7 papers for grad project	2nd April		4th Apr	1	Thurs
Presentation of initial background research	3rd April		5th Apr	1	Fri	Print off 7 papers on CRFs/RNNs
Find, print, and make notes from 5 papers on CRFs/RNNs			6th Apr	1	Sat	Make 2 week plan to present
Northstar background research and note taking			7th Apr	1	Sun	Build IMU .py scripts (graph and cluster functions)
Find, print, and make notes from 5 papers on time-series regression			8th Apr	2	Mon	Read / make notes from 1 paper
Type up notes thus far			9th Apr	2	Tues	Read / make notes from 1 paper	Read ML textbook, 19.0 – 19.6
			10th Apr	2	Wed	Go to meeting
			11th Apr	2	Thurs
			12th Apr	2	Fri	Python: add supervised learning functionality to IMU datasets	Python: setup git repo for project
			13th Apr	2	Sat
			14th Apr	2	Sun
			15th Apr	3	Mon
Project Tasks (17th Apr - 30th Apr; 2 weeks)			16th Apr	3	Tues
			17th Apr	3	Wed	Find further 5 papers relating to CRFs/RNNs and action/motion analysis	Create research papers folder and file previous papers
Find further 5 papers relating to CRFs/RNNs and action/motion analysis	17th Apr		18th Apr	3	Thurs	Setup laptop for CUDA / TF GPU	Read and complete programs in 'Python ML', ch 16
Create research papers folder and file previous papers	17th Apr		19th Apr	3	Fri	URL link review: “Overview of Conditional Random Fields”	URL link review: “Performing Sequence Labelling using CRF in Python”
Setup laptop for CUDA / TF GPU	18th Apr		20th Apr	3	Sat
Read and complete programs in 'Python ML', ch 16	18th Apr		21st Apr	3	Sun	URL link review: “Conditional Random Fields for Sequence Prediction”	URL link review: “Conditional Random Fields for Sequence Prediction”
URL link review: “Overview of Conditional Random Fields”	19th Apr		22nd Apr	4	Mon	Make RNN / CRF presentation (2 slides each, 1 description, 1 usefulness)
URL link review: “Performing Sequence Labelling using CRF in Python”	19th Apr		23rd Apr	4	Tues	Print and file: 'Feature learning papers', 'Medical stuff', 'RNN stuff', 'CRF stuff'	Paper review: “Conditional Random Fields for Activity Recognition in Smart Environments”
URL link review: “Conditional Random Field Tutorial in PyTorch”	21st Apr		24th Apr	4	Wed	Paper review: “Deep, Convolutional, and Recurrent Models for HAR using Wearables”	Do RNN / CRF presentation
URL link review: “Conditional Random Fields for Sequence Prediction”	21st Apr		25th Apr	4	Thurs	Go for 1-on-1 meeting
Make RNN / CRF presentation (2 slides each, 1 description, 1 usefulness)	22nd Apr		26th Apr	4	Fri
Print and file: 'Feature learning papers', 'Medical stuff', 'RNN stuff', 'CRF stuff'	23rd Apr		27th Apr	4	Sat
Paper review: “Conditional Random Fields for Activity Recognition in Smart Environments”	23rd Apr		28th Apr	4	Sun
Paper review: “Deep, Convolutional, and Recurrent Models for HAR using Wearables”	24th Apr		29th Apr	5	Mon
Do RNN / CRF presentation	24th Apr		30th Apr	5	Tues
Go for 1-on-1 meeting	25th Apr
Type up and make import points from: “Cond Random Fields: Prob Models for Sequencing”			1st May	5	Wed
Type up and make import points from: “CRFs as RNNs”			2nd May	5	Thurs
Paper review: “Action Categorization with Modified Hidden Conditional Random Field”			3rd May	5	Fri
Type up and make import points from: “CRFs for AR in Smart Environments”			4th May	5	Sat
Type up and make import points from: “Deep, Conv, and Recurrent Models for HAR”			5th May	5	Sun
Paper review: “Conditional Models for Contextual Human Motion Recognition”			6th May	6	Mon
Paper review: “Conditional Random People: Tracking Humans with CRFs and Grid Filters”			7th May	6	Tues
Paper review: “Actionness Ranking with Lattice Conditional Ordinal Random Fields”			8th May	6	Wed
Paper review: “Continuous Conditional Random Fields for Regression in Remote Sensing”			9th May	6	Thurs
Paper review: “Deep Convolutional and LSTM Recurrent NNs for Multimodal Wearable AR”			10th May	6	Fri
Paper review: “Deep Recurrent NN for Mobile HAR with High Throughput”			11th May	6	Sat
			12th May	6	Sun
			13th May	7	Mon
			14th May	7	Tues
			15th May	7	Wed
Paper review: “HAR and Pattern Discovery”			16th May	7	Thurs
Paper review: “A Comprehensive Study of Activity Recognition Using Accelerometers”			17th May	7	Fri
Paper review: “An Analysis of Single-Layer Networks in Unsupervised Feature Learning'			18th May	7	Sat
Paper review: “Simultaneous Feature Learning and Hash Coding with Deep Neural Networks”			19th May	7	Sun
Paper review: “Discriminative Unsupervised Feature Learning with CNNs”			20th May	8	Mon
Write 2-3 preliminary pages of report on background research and tasks undertaken			21st May	8	Tues
Type up and organize notes from papers (separate sections for CRF/RNN/feature learn, etc)			22nd May	8	Wed
URL link review: “Lecture 13: Variational Inference: Mean Field Approximation”			23rd May	8	Thurs
Read and take notes from 'Sequence Modeling: Recurrent and Recursive Nets'			24th May	8	Fri
			25th May	8	Sat
			26th May	8	Sun
			27th May	9	Mon
			28th May	9	Tues
			29th May	9	Wed
			30th May	9	Thurs
			31st May	9	Fri