## Sheet1
				Date	Week	Day	Coursera	MSc Project Tasks
				30th Mar	0	Sat		Read, make notes, and summarize from 2 papers
				31st Mar	0	Sun		Read, make notes, and summarize from 3 papers
				1st Apr	1	Mon
				2nd Apr	1	Tues		Read, make notes, and summarize from 2 papers
	MSc Project Tasks			3rd Apr	1	Wed		Presentation of initial background research
	Research and summarise from 7 papers for grad project	2nd April		4th Apr	1	Thurs
	Presentation of initial background research	3rd April		5th Apr	1	Fri		Print off 7 papers on CRFs/RNNs
	Find, print, and make notes from 5 papers on CRFs/RNNs			6th Apr	1	Sat		Make 2 week plan to present
	Northstar background research and note taking			7th Apr	1	Sun		Build IMU .py scripts (graph and cluster functions)
	Find, print, and make notes from 5 papers on time-series regression			8th Apr	2	Mon		Read / make notes from 1 paper
	Type up notes thus far			9th Apr	2	Tues		Read / make notes from 1 paper	Read ML textbook, 19.0 – 19.6
				10th Apr	2	Wed		Go to meeting
				11th Apr	2	Thurs
				12th Apr	2	Fri		Python: add supervised learning functionality to IMU datasets	Python: setup git repo for project
				13th Apr	2	Sat
				14th Apr	2	Sun
				15th Apr	3	Mon
Project time	Project Tasks			16th Apr	3	Tues
				17th Apr	3	Wed		Find further 5 papers relating to CRFs/RNNs and action/motion analysis	Create research papers folder and file previous papers
	Find further 5 papers relating to CRFs/RNNs and action/motion analysis	17th Apr		18th Apr	3	Thurs		Setup laptop for CUDA / TF GPU	Read and complete programs in 'Python ML', ch 16
	Create research papers folder and file previous papers	17th Apr		19th Apr	3	Fri		URL link review: “Overview of Conditional Random Fields”	URL link review: “Performing Sequence Labelling using CRF in Python”
	Setup laptop for CUDA / TF GPU	18th Apr		20th Apr	3	Sat
	Read and complete programs in 'Python ML', ch 16	18th Apr		21st Apr	3	Sun		URL link review: “Conditional Random Fields for Sequence Prediction”	URL link review: “Conditional Random Fields for Sequence Prediction”
	URL link review: “Overview of Conditional Random Fields”	19th Apr		22nd Apr	4	Mon		Make RNN / CRF presentation (2 slides each, 1 description, 1 usefulness)
	URL link review: “Performing Sequence Labelling using CRF in Python”	19th Apr		23rd Apr	4	Tues		Print and file: 'Feature learning papers', 'Medical stuff', 'RNN stuff', 'CRF stuff'	Paper review: “Conditional Random Fields for Activity Recognition in Smart Environments”
	URL link review: “Conditional Random Field Tutorial in PyTorch”	21st Apr		24th Apr	4	Wed		Paper review: “Deep, Convolutional, and Recurrent Models for HAR using Wearables”	Do RNN / CRF presentation
	URL link review: “Conditional Random Fields for Sequence Prediction”	21st Apr		25th Apr	4	Thurs		Go for 1-on-1 meeting
	Make RNN / CRF presentation (2 slides each, 1 description, 1 usefulness)	22nd Apr		26th Apr	4	Fri		Type up and make import points from: “Cond Random Fields: Prob Models for Sequencing”	Type up and make import points from: “CRFs as RNNs”	Paper review: “Action Categorization with Modified Hidden Conditional Random Field”
	Print and file: 'Feature learning papers', 'Medical stuff', 'RNN stuff', 'CRF stuff'	23rd Apr		27th Apr	4	Sat		Type up and make import points from: “CRFs for AR in Smart Environments”	Type up and make import points from: “Deep, Conv, and Recurrent Models for HAR using Wearables”
	Paper review: “Conditional Random Fields for Activity Recognition in Smart Environments”	23rd Apr		28th Apr	4	Sun		Paper review: “Deep Recurrent NN for Mobile HAR with High Throughput”	Find, print, file, and make plan for papers regarding RNNs for HAR	Paper review: “Hidden CRFs for Gesture Recognition”
	Paper review: “Deep, Convolutional, and Recurrent Models for HAR using Wearables”	24th Apr		29th Apr	5	Mon
	Do RNN / CRF presentation	24th Apr		30th Apr	5	Tues		Paper review: “Hierarchical Recurrent Neural Network for Skeleton Based Action Recognition”	Programming: Download/setup suit data and create diffs plot function
	Go for 1-on-1 meeting	25th Apr
	Type up and make import points from: “Cond Random Fields: Prob Models for Sequencing”	26th Apr		1st May	5	Wed		Paper review: “Continuous Conditional Random Fields for Regression in Remote Sensing”	Programming: add function to extract statistical features of joint files + print results to separate .csv
	Type up and make import points from: “CRFs as RNNs”	26th Apr		2nd May	5	Thurs		Type up and make import points from: “Action Categorization with Modified Hidden CRF”	Programming: create extract/dynamic visualisation functions for all-data files
	Paper review: “Action Categorization with Modified Hidden Conditional Random Field”	26th Apr		3rd May	5	Fri		Programming: setup classes for different file types, comment all code, and commit
	Type up and make import points from: “CRFs for AR in Smart Environments”	27th Apr		4th May	5	Sat	Data engin, c1, w1, m1 – m2	Programming: create AD function for accel/magnet/position statistical analysis	Type up and make import points from: “Deep Recurrent NN for Mobile HAR with High Throughput”	Type up and make import points from: “Hidden CRFs for Gesture Recognition”
	Type up and make import points from: “Deep, Conv, and Recurrent Models for HAR using Wearables”	27th Apr		5th May	5	Sun	Data engin, c1, w1, m3	Programming: add to DC init function (inc extract table to .csv and read in, and passing to JA objects)	Programming: add Fourier analysis functionality to statistical extraction for AD class (veloc+accel)	Type up and make import points from: “Hierarchical Recurrent Neural Network for Skeleton Based AR”
	Paper review: “Deep Recurrent NN for Mobile HAR with High Throughput”	28th Apr		6th May	6	Mon		Type up and make import points from: “Continuous CRFs for Regression in Remote Sensing”	Make presentation of 2 weeks inc: suit data format, .py script, next steps
	Find, print, file, and make plan for papers regarding RNNs for HAR	28th Apr		7th May	6	Tues	Data engin, c1, w1, m4	Program: swap order of col label to be: measure, feature, axis, stat	Program: create dict mapping from measure name to seg/joint/sens names	Program: add command line functionality and arguments	Program: fix crashes-on-close problem with pyplot windows
	Paper review: “Hidden CRFs for Gesture Recognition”	28th Apr		8th May	6	Wed		Go to group meeting
	Paper review: “Hierarchical Recurrent Neural Network for Skeleton Based Action Recognition”	30th Apr		9th May	6	Thurs		Add name of file to output col (i.e. one col for if HC or D file)
	Programming: Download/setup suit data and create diffs plot function	30th Apr		10th May	6	Fri
	Paper review: “Continuous Conditional Random Fields for Regression in Remote Sensing”	1st May		11th May	6	Sat		Add option to 'split up the input JA/AD file w/ 'HC'/'D' labels into numerous files w/ same label	Add function that checks for behaviour abnormality over all features for each file written
	Programming: add function to extract statistical features of joint files + print results to separate .csv	1st May		12th May	6	Sun	Data engin, c1, w1, m5 (2/3)
	Type up and make import points from: “Action Categorization with Modified Hidden CRF”	2nd May		13th May	7	Mon		Implement 'extract_stat_features' function to be called by write_stats by both classes including all stat functions	Implement function to extract JA .mat files to .csv	Add other stat features (see paper for full list of features to additionally include)	Make display 3D pos plot run in real-time
	Programming: create extract/dynamic visualisation functions for all-data files	2nd May		14th May	7	Tues	Data engin, c1, w1, m5-7	Implement basic RNN model with .csv output file
	Programming: setup classes for different file types, comment all code, and commit	3rd May		15th May	7	Wed		Group meeting
	Programming: create AD function for accel/magnet/position statistical analysis	4th May		16th May	7	Thurs	Data engin, c2, w1, m1	Create README file of 'matfile_analysis'	Edit RNN layout and suppress warnings on output	Add optional argument to automatically delete the created output .csv files at end of command	Eliminate need for 'file name' when 'file type' given as 'dc'
	Type up and make import points from: “Deep Recurrent NN for Mobile HAR with High Throughput”	4th May		17th May	7	Fri
	Type up and make import points from: “Hidden CRFs for Gesture Recognition”	4th May		18th May	7	Sat		Ensure different file types are written to different subdirectories of 'output_files' (e.g. for AD, JA, DC)	Add alternative to 'split files' in matfiles_analysis that specifies a preferred file length rather than num of splits
	Programming: add to DC init function (inc extract table to .csv and read in, and passing to JA objects)	5th May		19th May	7	Sun
	Programming: add Fourier analysis functionality to statistical extraction for AD class (veloc+accel)	5th May		20th May	8	Mon
	Type up and make import points from: “Hierarchical Recurrent Neural Network for Skeleton Based AR”	5th May		21st May	8	Tues
	Type up and make import points from: “Continuous CRFs for Regression in Remote Sensing”	6th May		22nd May	8	Wed
	Make presentation of 2 weeks inc: suit data format, .py script, next steps	6th May		23rd May	8	Thurs
	Program: swap order of col label to be: measure, feature, axis, stat	7th May		24th May	8	Fri
	Program: create dict mapping from measure name to seg/joint/sens names	7th May		25th May	8	Sat
	Program: add command line functionality and arguments	7th May		26th May	8	Sun
	Program: fix crashes-on-close problem with pyplot windows	7th May		27th May	9	Mon
	Go to group meeting	8th May		28th May	9	Tues
	Add name of file to output col (i.e. one col for if HC or D file)	9th May		29th May	9	Wed
	Add option to 'split up the input JA/AD file w/ 'HC'/'D' labels into numerous files w/ same label	11th May		30th May	9	Thurs
	Add function that checks for behaviour abnormality over all features for each file written	11th May		31st May	9	Fri
	Implement 'extract_stat_features' function to be called by write_stats by both classes including all stat functions	13th May
	Implement function to extract JA .mat files to .csv	13th May
	Add other stat features (see paper for full list of features to additionally include)	13th May
	Make display 3D pos plot run in real-time	13th May
	Implement basic RNN model with .csv output file	14th May
	Group meeting	15th May
	Create README file of 'matfile_analysis'	16th May
	Edit RNN layout and suppress warnings on output	16th May
	Add optional argument to automatically delete the created output .csv files at end of command	16th May
	Eliminate need for 'file name' when 'file type' given as 'dc'	16th May
	Ensure different file types are written to different subdirectories of 'output_files' (e.g. for AD, JA, DC)	18th May
	Add alternative to 'split files' in matfiles_analysis that specifies a preferred file length rather than num of splits	18th May
	Modify 'matfiles_analysis' to work with diff subdirs	20th May
	Download additional necessary dataset files	20th May
	Comment both scripts	20th May
	Add script with various feature reduction techniques	21st May
	Add option to read in NSS's into df as new column	21st May
	Implement NSS as labels in RNN script	21st May
	Adapt RNN to predict north star scores as alternative	22nd May
	Group meeting	22nd May
	Add functionality to extract act scores from .xlxs into df	23rd May
	Add batch script	24th May
	Group meeting	24th May
	Annotate D11-D20 NSAA files and edit google sheet	30th May
	Fix issue with 'JA/DC all' split_size=1 only showing '19s' on 'y-true'	30th May
	Add function in RNN to write real and predicted scores to .csv	31st May
	Create 'mat_act_div' script to divide up .mat files and rewrite to new dir	31st May
	Fix 3D image pos not ending and exiting issue	31st May
	Fix 3D image pos distortion issue	31st May
	Use 'mat_an' to setup 'NSAA\AD', '6minwalk-matfiles\AD', 'direct_csv\DC', and 'direct_csv\JA'	1st June
	Modify 'ft_red' to work with 'fn=all' argument and encapsulate feature selection/reduction	1st June
	Modify RNN to work with both stat vals and raw joint angles for both DMD/HC class and NSAA regress	1st June
	Create .csv file with results of RNN setups (DMD/HC class and NSAA regress for both AD and DC raw joint files)	1st June
	Change names of all scripts and put them in 'source' directory (alter output dirs and batch as needed)	2nd June
	Add to 'RNN results' for '6minwalk-matfiles\AD' and 'direct_csv\JA' for both choice='dhc' and 'overall'	2nd June
	Modify RNN to predict 17 output nodes for each activity w/ AD files from NSAA	2nd June
	Add optional argument to 'rnn' to write results and settings to relevant columns in 'RNN Results.ods'	2nd June
	Write presentation for group meeting	3rd June
	Add optional argument to 'comp_stat_vals' to write all files to one 'all' file	4th June
	Add 'ext_raw_measures' script to extract specific raw measurement values from given AD .mat file(s)	4th June
	Group meeting and presentation	5th June
	Init report: section on next steps + further aims	5th June
	Init report: section on data pipeline and data file types	5th June
	Init report: section on RNN output formats	5th June
	Init report: summarize results table	5th June
	Init report: attach all scripts to appendices	6th June
	Init report: outline preprocess work done	6th June
	Init report: section on theory/practical of RNN	6th June
	Init report: background on DMD/NSAA + project motivation	6th June
	Init report: add papers to bibliography	7th June
	Init report: add cover sheet and introduction	7th June
	Init report: section on theory/practical of CRF	7th June
	Init report: write literature review	7th June
	Init report: edit and submit report	7th June
	Create new list of tasks from initial report, most-recent presentation, and paper note	7th June
	Add R^2 and RMSE as metrics in 'RNN.py' for regression	8th June
	Implement confusion matrix output in 'RNN.py' for D/HC classification	8th June
	Experiment for all input options for choice='acts'	8th June
	Add optional argument to 'RNN.py' to specify proportion of sequence overlap	8th June
	Add 'all' option for 'measurements' in 'ext_raw_measures.py' and run script with 'measurements=all'	8th June
	Modify 'RNN.py' to work with raw measurements from local drive	8th June
	Modify 'add_nsaa_scores' in both scripts to read NSAA scores from 'KineDMD data updates Feb 2019'	9th June
	Change 'model_dir' to reflect script arguments	9th June
	Add 'RNN.py' results output to 'write_to_csv'	9th June
	Add optional 'RNN.py' argument to set num_epochs as argument	9th June
	Experiment with different raw data measurements from AD files for various RNN outputs	10th June
	Experiment with various sequence overlap proportion for NSAA\AD stat vals for choice='overall'	10th June
	Enable 'comp_stat_vals' to extract features from 'single-act' matfiles	11th June
	Enable 'ext_raw_measures' to work with 'single-act' matfiles and extract all measures from 'single-act' files	11th June
	Modify 'RNN.py' to work with single-act .mat files to predict single-act NSAA scores	11th June
	Add a README for 'How to use 3D visualization function'	12th June
	Group meeting	12th June
	Comment 'mat_act_div.py' and 'ext_raw_measures.py' scripts	15th June
	Download missing files from 'NSAA\matfiles\ directory	15th June
	Create .csv file with all subject info from 3 prev files	15th June
	Experiment with single-act raw measurements files to predict single-act score (0, 1, or 2)	15th June
	Move 'output_files' off dropbox into 'msc_project_files' and have all scripts point to there	15th June
	Write script that loads a trained RNN model and tests on a complete file	16th June
	Comment 'rnn.py' and 'ft_sel_red.py' scripts	18th June
	Experiment w/ useful raw measurements with longer sequences and larger sequence overlap	18th June
	Modify pipeline to ensure ALL available files are processed (w/ lowercase + 'V2' considered and fix 'all 2's' single acts issue)	18th June
	Change both 'add_nsaa_scores' to only use 'nsaa_6mw_matfiles'	19th June
	Add more experiments with longer seq length and more raw measurements	19th June
	Download the additional 'NSAA\matfiles'	19th June
	Write script to create matplotlib graphs from lines in 'RNN Results'	20th June
	Rerun NSAA stat vales pipeline with new files	20th June
	Ensure 'model_predictor' works with stat vals output	21st June
	Modify 'rnn' and 'model_predictor' to use .xlsx file for storing seq_len	21st June
	Ensure 'graph_creator' withs with all expers and choices, and rerun	21st June
	Run experiments w/ 'NSAA\AD' diff features and plot graphs	22nd June
	Run experiments w/ 'NSAA\AD' different seq len and overlaps and plot graphs	22nd June
	Modify 'ft_sel_red' to always delete previous 'FT_' files in directory	22nd June
	Make slides of purpose of project, diagram of all scripts, experiments + results thus far, and next steps	22nd June
	Do the video annotations required and fill out the Google sheet	22nd June
	Add option in 'model_predictor' to create ensemble of various raw measurements and stat values	23rd June
	Fix 'rnn.py' to write to 'model_shapes'	23rd June
	Fix 'model_predictor' to work w/ AD files	23rd June
	Add option to 'rnn.py' to create graph of real vs predicted overall NSAA scores	25th June
	Make 'write_to_csv' write to unique files based on args/epochs and a unique index number	25th June
	Modify 'ext_raw_measures' to extract 'allmatfiles' files and run	25th June
	Experiment w/ AD files w/ shorter seq_lens for AD and graph results	27th June
	Add '--discard_prop' option to 'rnn' to optionally discard every nth element to reduce size of sequence length while keeping context high	27th June
	Experiment w/ longer seq_lens and discard_prop for jointAngle and graph results	27th June
	Add option to 'graph_creator.py' to create graph of trues vs preds overall NSAA scores from single file name arg	27th June
	Modify 'model_predictor.py' to round overall NSAA scores after averaging across models	27th June
	Write batch script to work with a single 'allmatfiles' or AD file and feed through to 'model_predictor' (w/ modified to work with 'allmatfiles' files)	27th June
	Group meeting	27th June
	Modify 'model_predictor.py' to write and display trues/preds graph	28th June
	Write batch script to do all package setup and run 'comp_stat_vals', 'ft_sel_red', ext_raw_measures'. 'mat_act_div' (w/ all source dirs)	28th June
	Modify 'file_predictor.cmd' to work with AD source files through pipeline	28th June
	Add optional 'rnn.py' argument to use additional source dir along with current 'dir' to combine 6minwalk and 6MW	1st July
	Add optional 'rnn.py' argument to leave a file out (i.e. '--leave_out=D10' means model is trained on all files EXCEPT 'D10') w/ 'model_dir' modified too	1st July
	Run 'rnn.py' w/ NSAA top-4 raw measurements and AD for all output types with most ideal seq_len, seq_overlap, discard_prop, epochs, etc	1st July
	Reorganize batch scripts into subdir of 'source'	2nd July
	Run 'rnn.py' w/ combined 6minwalk and 6MW w/ same data types, output types, etc. as with NSAA	2nd July
	Group meeting	3rd July

	List of Tasks (5th - 14th July)	Date Completed

	Programming
	Change RNN_outputs .csv name to be based on sys.argsv	5th July
	Add optional 'alt_dirs' argument to 'model_predictor' to use different directory(s) to test the file on	5th July
	Create 'file_predictor_altdirs.cmd' to load an 'allmatfile' file and test it on the NSAA\jointAngle and 6m\jointAngle models	5th July
	Modify 'model_predictor.py' to write 'output_strs' to a single test file (each model = 1 row, each string = 1 col of row)	6th July
	Write 'test_altdirs' script that automates the testing of each file in a dir on different dirs	6th July
	Add option to 'graph_creator.py' to graph the results in 'model_predictions.csv'	6th July
	Write script that stores all global variables used across files ('local_dir', 'source_dir', 'file_types', etc.) and modify other scripts
	Write script to standardize names of 'mat' files in source directories, add to 'setup.cmd', run on all source dirs, and run all lines in 'setup.cmd'
	Write batch script to train an RNN with given file left out then run model predictor on that file
	Write script of basic CRF model with .csv output file of statistical values

	Experiments
	Experiment w/ all 'allmatfiles' files using 'test_altdirs.py' w/ models trained on both NSAA and 6MW and graph results	6th July
	Experiment w/ 'left out' batch script with various left-out files (i.e. having retrained RNN w/ leaving out one file each time) and record the results
	Experiment w/ single-act files trained to approximate overall NSAA score and rank best performing acts w.r.t MSE

	Deliverables
	Write complete results discussion of all results and experiment sets in more detail (5-6 pages, not including graphs in appendices)
	Add general README to GitHub repo outlining the project and how the repo is laid out
	Add README for each of the source files and modify the existing one for 'comp_stat_vals'
	Write complete script ecosystem discussion, including powerpoint diagram and heavily using READMEs for each source script
	Write complete literature review covering all previously reviewed and recently reviewed papers

	Paper Reviews
	Paper review + type: “Co-Occurrence Feature Learning for Skeleton Based AR using Regularized DLSTM Networks”
	Paper review + type: “Differential RNNs for Action Recognition”
	Paper review + type: “Online Detection and Classification of Dynamic Hand Gestures with Recurrent 3D CNNs”
	Paper review + type: “Long-term Recurrent Convolutional Networks for Visual Recognition and Description”
	Paper review + type: “Sequential Deep Learning for Human Action Recognition”
	Paper review + type: “Spatio-Temporal LSTM with Trust Gates for 3D HAR”
	Paper review + type: “Deep Convolutional and LSTM Recurrent NNs for Multimodal Wearable AR”
	Paper review + type: “Conditional Random People: Tracking Humans with CRFs and Grid Filters”
	Paper review + type: “Actionness Ranking with Lattice Conditional Ordinal Random Fields”
	Paper review + type: “Conditional Models for Contextual Human Motion Recognition”

	Paper Reviews
	Review previous papers: “CRFs – Prob models...” and “CRFs as RNNs”
	Review previous papers: “CRFs for AR...” and “Action Categ...”
	Review previous papers: “Hidden CRFs...” and “Continuous CRFs...”
	Review previous papers: “Deep, conv...”, “Deep RNN...”, and “Hierarch RNN...”
	Paper review: “A Comprehensive Study of Activity Recognition Using Accelerometers”
	Paper review: “An Analysis of Single-Layer Networks in Unsupervised Feature Learning'
	Paper review: “Simultaneous Feature Learning and Hash Coding with Deep Neural Networks”
	Paper review: “Discriminative Unsupervised Feature Learning with CNNs”
	Write 2-3 preliminary pages of report on background research and tasks undertaken
	Type up and organize notes from papers (separate sections for CRF/RNN/feature learn, etc)
	URL link review: “Lecture 13: Variational Inference: Mean Field Approximation”
	Read and take notes from 'Sequence Modeling: Recurrent and Recursive Nets'