## Sheet1
				1st - 7th April	8th - 14th April	15th - 21st April	22nd - 28th April
MSc Project Tasks			Stage	Task	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8
	2nd April		1: Background Research and Setup	Research + summarise from 7 papers
	3rd April			Presentation of initial background research
				Find + make notes from 5 papers on RNNs
				Northstar background research and note taking
				Type up notes thus far
				Find further 5 papers relating to RNNs and action/motion analysis
				Create research papers folder and file previous papers
				Setup laptop for CUDA / TF GPU
				Read and complete programs in 'Python ML', ch 16
				Make RNN / CRF presentation (2 slides each, 1 description, 1 usefulness)
				Paper review: “Deep, Convolutional, and Recurrent Models for HAR using Wearables”
				Do RNN presentation
Project Tasks

			Stage	Task	Week 9	Week 10	Week 11	Week 12	Week 13	Week 14	Week 15	Week 16

Do RNN / CRF presentation	24th Apr
Go for 1-on-1 meeting	25th Apr
Type up and make import points from: “Cond Random Fields: Prob Models for Sequencing”	26th Apr
Type up and make import points from: “CRFs as RNNs”	26th Apr
Paper review: “Action Categorization with Modified Hidden Conditional Random Field”	26th Apr
Type up and make import points from: “CRFs for AR in Smart Environments”	27th Apr
Type up and make import points from: “Deep, Conv, and Recurrent Models for HAR using Wearables”	27th Apr
Paper review: “Deep Recurrent NN for Mobile HAR with High Throughput”	28th Apr
Find, print, file, and make plan for papers regarding RNNs for HAR	28th Apr
Paper review: “Hidden CRFs for Gesture Recognition”	28th Apr
Paper review: “Hierarchical Recurrent Neural Network for Skeleton Based Action Recognition”	30th Apr
Programming: Download/setup suit data and create diffs plot function	30th Apr
Paper review: “Continuous Conditional Random Fields for Regression in Remote Sensing”	1st May
Programming: add function to extract statistical features of joint files + print results to separate .csv	1st May		Stage	Task	Week 17	Week 18	Week 19	Week 20	Week 21	Week 22	Week 23
Type up and make import points from: “Action Categorization with Modified Hidden CRF”	2nd May
Programming: create extract/dynamic visualisation functions for all-data files	2nd May
Programming: setup classes for different file types, comment all code, and commit	3rd May
Programming: create AD function for accel/magnet/position statistical analysis	4th May
Type up and make import points from: “Deep Recurrent NN for Mobile HAR with High Throughput”	4th May
Type up and make import points from: “Hidden CRFs for Gesture Recognition”	4th May
Programming: add to DC init function (inc extract table to .csv and read in, and passing to JA objects)	5th May
Programming: add Fourier analysis functionality to statistical extraction for AD class (veloc+accel)	5th May
Type up and make import points from: “Hierarchical Recurrent Neural Network for Skeleton Based AR”	5th May
Type up and make import points from: “Continuous CRFs for Regression in Remote Sensing”	6th May
Make presentation of 2 weeks inc: suit data format, .py script, next steps	6th May
Program: swap order of col label to be: measure, feature, axis, stat	7th May
Program: create dict mapping from measure name to seg/joint/sens names	7th May
Program: add command line functionality and arguments	7th May
Program: fix crashes-on-close problem with pyplot windows	7th May
Go to group meeting	8th May
Add name of file to output col (i.e. one col for if HC or D file)	9th May
Add option to 'split up the input JA/AD file w/ 'HC'/'D' labels into numerous files w/ same label	11th May
Add function that checks for behaviour abnormality over all features for each file written	11th May
Implement 'extract_stat_features' function to be called by write_stats by both classes including all stat functions	13th May
Implement function to extract JA .mat files to .csv	13th May
Add other stat features (see paper for full list of features to additionally include)	13th May
Make display 3D pos plot run in real-time	13th May
Implement basic RNN model with .csv output file	14th May
Group meeting	15th May
Create README file of 'matfile_analysis'	16th May
Edit RNN layout and suppress warnings on output	16th May
Add optional argument to automatically delete the created output .csv files at end of command	16th May
Eliminate need for 'file name' when 'file type' given as 'dc'	16th May
Ensure different file types are written to different subdirectories of 'output_files' (e.g. for AD, JA, DC)	18th May
Add alternative to 'split files' in matfiles_analysis that specifies a preferred file length rather than num of splits	18th May
Modify 'matfiles_analysis' to work with diff subdirs	20th May
Download additional necessary dataset files	20th May
Comment both scripts	20th May
Add script with various feature reduction techniques	21st May
Add option to read in NSS's into df as new column	21st May
Implement NSS as labels in RNN script	21st May
Adapt RNN to predict north star scores as alternative	22nd May
Group meeting	22nd May
Add functionality to extract act scores from .xlxs into df	23rd May
Add batch script	24th May
Group meeting	24th May
Annotate D11-D20 NSAA files and edit google sheet	30th May
Fix issue with 'JA/DC all' split_size=1 only showing '19s' on 'y-true'	30th May
Add function in RNN to write real and predicted scores to .csv	31st May
Create 'mat_act_div' script to divide up .mat files and rewrite to new dir	31st May
Fix 3D image pos not ending and exiting issue	31st May
Fix 3D image pos distortion issue	31st May
Use 'mat_an' to setup 'NSAA\AD', '6minwalk-matfiles\AD', 'direct_csv\DC', and 'direct_csv\JA'	1st June
Modify 'ft_red' to work with 'fn=all' argument and encapsulate feature selection/reduction	1st June
Modify RNN to work with both stat vals and raw joint angles for both DMD/HC class and NSAA regress	1st June
Create .csv file with results of RNN setups (DMD/HC class and NSAA regress for both AD and DC raw joint files)	1st June
Change names of all scripts and put them in 'source' directory (alter output dirs and batch as needed)	2nd June
Add to 'RNN results' for '6minwalk-matfiles\AD' and 'direct_csv\JA' for both choice='dhc' and 'overall'	2nd June
Modify RNN to predict 17 output nodes for each activity w/ AD files from NSAA	2nd June
Add optional argument to 'rnn' to write results and settings to relevant columns in 'RNN Results.ods'	2nd June
Write presentation for group meeting	3rd June
Add optional argument to 'comp_stat_vals' to write all files to one 'all' file	4th June
Add 'ext_raw_measures' script to extract specific raw measurement values from given AD .mat file(s)	4th June
Group meeting and presentation	5th June
Init report: section on next steps + further aims	5th June
Init report: section on data pipeline and data file types	5th June
Init report: section on RNN output formats	5th June
Init report: summarize results table	5th June
Init report: attach all scripts to appendices	6th June
Init report: outline preprocess work done	6th June
Init report: section on theory/practical of RNN	6th June
Init report: background on DMD/NSAA + project motivation	6th June
Init report: add papers to bibliography	7th June
Init report: add cover sheet and introduction	7th June
Init report: section on theory/practical of CRF	7th June
Init report: write literature review	7th June
Init report: edit and submit report	7th June
Create new list of tasks from initial report, most-recent presentation, and paper note	7th June
Add R^2 and RMSE as metrics in 'RNN.py' for regression	8th June
Implement confusion matrix output in 'RNN.py' for D/HC classification	8th June
Experiment for all input options for choice='acts'	8th June
Add optional argument to 'RNN.py' to specify proportion of sequence overlap	8th June
Add 'all' option for 'measurements' in 'ext_raw_measures.py' and run script with 'measurements=all'	8th June
Modify 'RNN.py' to work with raw measurements from local drive	8th June
Modify 'add_nsaa_scores' in both scripts to read NSAA scores from 'KineDMD data updates Feb 2019'	9th June
Change 'model_dir' to reflect script arguments	9th June
Add 'RNN.py' results output to 'write_to_csv'	9th June
Add optional 'RNN.py' argument to set num_epochs as argument	9th June
Experiment with different raw data measurements from AD files for various RNN outputs	10th June
Experiment with various sequence overlap proportion for NSAA\AD stat vals for choice='overall'	10th June
Enable 'comp_stat_vals' to extract features from 'single-act' matfiles	11th June
Enable 'ext_raw_measures' to work with 'single-act' matfiles and extract all measures from 'single-act' files	11th June
Modify 'RNN.py' to work with single-act .mat files to predict single-act NSAA scores	11th June
Add a README for 'How to use 3D visualization function'	12th June
Group meeting	12th June
Comment 'mat_act_div.py' and 'ext_raw_measures.py' scripts	15th June
Download missing files from 'NSAA\matfiles\ directory	15th June
Create .csv file with all subject info from 3 prev files	15th June
Experiment with single-act raw measurements files to predict single-act score (0, 1, or 2)	15th June
Move 'output_files' off dropbox into 'msc_project_files' and have all scripts point to there	15th June
Write script that loads a trained RNN model and tests on a complete file	16th June
Comment 'rnn.py' and 'ft_sel_red.py' scripts	18th June
Experiment w/ useful raw measurements with longer sequences and larger sequence overlap	18th June
Modify pipeline to ensure ALL available files are processed (w/ lowercase + 'V2' considered and fix 'all 2's' single acts issue)	18th June
Change both 'add_nsaa_scores' to only use 'nsaa_6mw_matfiles'	19th June
Add more experiments with longer seq length and more raw measurements	19th June
Download the additional 'NSAA\matfiles'	19th June
Write script to create matplotlib graphs from lines in 'RNN Results'	20th June
Rerun NSAA stat vales pipeline with new files	20th June
Ensure 'model_predictor' works with stat vals output	21st June
Modify 'rnn' and 'model_predictor' to use .xlsx file for storing seq_len	21st June
Ensure 'graph_creator' withs with all expers and choices, and rerun	21st June
Run experiments w/ 'NSAA\AD' diff features and plot graphs	22nd June
Run experiments w/ 'NSAA\AD' different seq len and overlaps and plot graphs	22nd June
Modify 'ft_sel_red' to always delete previous 'FT_' files in directory	22nd June
Make slides of purpose of project, diagram of all scripts, experiments + results thus far, and next steps	22nd June
Do the video annotations required and fill out the Google sheet	22nd June
Add option in 'model_predictor' to create ensemble of various raw measurements and stat values	23rd June
Fix 'rnn.py' to write to 'model_shapes'	23rd June
Fix 'model_predictor' to work w/ AD files	23rd June
Add option to 'rnn.py' to create graph of real vs predicted overall NSAA scores	25th June
Make 'write_to_csv' write to unique files based on args/epochs and a unique index number	25th June
Modify 'ext_raw_measures' to extract 'allmatfiles' files and run	25th June
Experiment w/ AD files w/ shorter seq_lens for AD and graph results	27th June
Add '--discard_prop' option to 'rnn' to optionally discard every nth element to reduce size of sequence length while keeping context high	27th June
Experiment w/ longer seq_lens and discard_prop for jointAngle and graph results	27th June
Add option to 'graph_creator.py' to create graph of trues vs preds overall NSAA scores from single file name arg	27th June
Modify 'model_predictor.py' to round overall NSAA scores after averaging across models	27th June
Write batch script to work with a single 'allmatfiles' or AD file and feed through to 'model_predictor' (w/ modified to work with 'allmatfiles' files)	27th June
Group meeting	27th June
Modify 'model_predictor.py' to write and display trues/preds graph	28th June
Write batch script to do all package setup and run 'comp_stat_vals', 'ft_sel_red', ext_raw_measures'. 'mat_act_div' (w/ all source dirs)	28th June
Modify 'file_predictor.cmd' to work with AD source files through pipeline	28th June
Add optional 'rnn.py' argument to use additional source dir along with current 'dir' to combine 6minwalk and 6MW	1st July
Add optional 'rnn.py' argument to leave a file out (i.e. '--leave_out=D10' means model is trained on all files EXCEPT 'D10') w/ 'model_dir' modified too	1st July
Run 'rnn.py' w/ NSAA top-4 raw measurements and AD for all output types with most ideal seq_len, seq_overlap, discard_prop, epochs, etc	1st July
Reorganize batch scripts into subdir of 'source'	2nd July
Run 'rnn.py' w/ combined 6minwalk and 6MW w/ same data types, output types, etc. as with NSAA	2nd July
Group meeting	3rd July
Change RNN_outputs .csv name to be based on sys.argsv	5th July
Add optional 'alt_dirs' argument to 'model_predictor' to use different directory(s) to test the file on	5th July
Create 'file_predictor_altdirs.cmd' to load an 'allmatfile' file and test it on the NSAA\jointAngle and 6m\jointAngle models	5th July
Modify 'model_predictor.py' to write 'output_strs' to a single test file (each model = 1 row, each string = 1 col of row)	6th July
Write 'test_altdirs' script that automates the testing of each file in a dir on different dirs	6th July
Add option to 'graph_creator.py' to graph the results in 'model_predictions.csv'	6th July
Experiment w/ all 'allmatfiles' files using 'test_altdirs.py' w/ models trained on both NSAA and 6MW and graph results	6th July
Write 'settings' script that stores all global variables used across files ('local_dir', 'source_dir', 'file_types', etc.) and modify other scripts	7th July
Write 'file_renamer' script to standardize names of 'mat' files in source directories and add to 'setup.cmd'	7th July
Write batch script to train RNNs with given file left out then run model predictor on that file	7th July
Add option to 'model_predictor.py' to use models that were specifically trained on for given 'fn' (even if corresponding '--leave_out='s exists)	8th July
Experiment w/ 'left out' batch script with left-out 'D3' files (i.e. having retrained RNN w/ leaving out 'D3' files each time) and record the results	8th July
Add script READMEs for 'settings', 'file_renamer', and 'test_altdirs'	8th July
Modify 'comp_stat_vals.py' so files aren't overwritten w/ diff sub-files (i.e. 'D2-003' doesn't overwrite 'D2-002's 'AD_D2_stat_features' file)	9th July
Download all '6minwalk-matfiles', '6MW-matFiles', and 'NSAA' files and run 'setup.cmd'	9th July
Modify 'model_predictor.py' to work with single-act files	9th July
Fix issues w/ 'model_predictions' not being written correctly and rerun 'allmatfiles on NSAA,6minwalk' and 'D3' on seen, unseen, and unseen w/ only 1 measure	10th July
Modify 'graph_creator.py' that reads in 'model_predictions' and computes statistical values over all lines that have just been written	10th July
Add script READMEs for 'mat_act_div' and 'ft_sel_red'	10th July
Add script README for 'ext_raw_measures'	13th July
Write 'data_balancer.py' script to balance datasets and have before and after counts of y-labels (all outputs) printed to output	14th July
Modify 'model_predictor' to ensure that non-balanced and non-left out models are used when appropriate	14th July
Refactor 'graph_creator with everything in functions and more appropriate arguments (1st arg = choice of functions to call)	14th July
Add function to 'graph_creator' to, for a given file, plot results of single-act predictions (3 graphs, 1 for each output, x-axis=act num) and run	14th July
Experiment w/ single-act 'D11' files tested on 'D11-left-out' models to approximate overall NSAA score	14th July
Add script README for 'graph_creator'	16th July
Experiment w/ up and down balanced datasets for left-out 'D3' file on models for all outputs and record the results (w/ larger or smaller overlap to compensate)	17th July
Experiment w/ left-out 'D11' natural movement files to train the 3 models	17th July
Add general README to GitHub repo outlining the project and how the repo is laid out	22nd July
Add script README for 'data_balancer'	22nd July
Update powerpoint diagram and add to script ecosystem overview and GitHub 'source' 'README.md'	22nd July
Write results discussion of experiment sets 1 - 2	22nd July
Write results discussion of experiment sets 3 - 4	23rd July
Add script README for 'rnn'	23rd July
Download additional data files, modify pipeline for new 'left-out' dir, and use it on each of these	23rd July
Add script README for 'model_predictor'	23rd July
Add script README covering all batch files	24th July
Write script discussion w/ copy-paste of script READMEs and include updated powerpoint diagram w/ script ecosystem overview	24th July
Group meeting	25th July
Write results discussion of experiment sets 5 – 8	26th July
Add table of details for experiments 1 – 8	26th July
Write results discussion for experiments 82 - 98	27th July
Write results discussion of 'model_predictions' for 'altdirs'	27th July
Write results discussion of 'model_predictions' for 'left-out' models	27th July

Week 1: List of Tasks (29th July - 4th Aug)	Date Completed

Download new Google sheet and modify 'mat_act_div.py' to use this instead of previous one (reference file names of sheet not subject names) and run	29th Jul
Add optional arg to 'mat_act_div.py' to create source files with single acts but concatenated together and run to produce in separate dir	29th Jul

Add optional arg to 'ft_sel_red' to reduce dimensions on whole dataset, rather than on file by file basis and run	30th Jul
Modify and run 'comp_stat_vals' and 'ext_raw_measures' on single_act concat and non-concat files	30th Jul
Modify 'rnn.py' and 'model_predictor.py' to use 'single_acts_concat' files and differently feature-reduced dataset	30th Jul
Write 'predictions_selector' script that reads 'model_predictions.csv' with given arguments to select certain subsets of rows and return certain good lines	30th Jul

Add 'cnn_preprocessing' function to 'rnn.py'	1st Aug

Build CNN models on 'D3', 'D9', 'D11', 'D17', 'HC6' left-out subjects, and provide 'rnn_outputs' results	2nd Aug
Modify reference table w/ correct 'D2'/'D3' entries and re-run all setup lines that make use of this file	2nd Aug
Add README script for 'predictions_selector', add it to script explanations, and modify pipeline diagrams	2nd Aug

Add optional args to 'rnn.py' to standardize all features of data prior to breaking it into sequences and add Gaussian noise to the dataset	3rd Aug
Restructure 'plans_and_presentations' and 'project_files' dirs into outer dir, put batch files into separate inner-'source' dir, and modify .py and .cmd scripts	3rd Aug
Report: write summary of use of Python, IDE, and TensorFlow	3rd Aug
Build standard 'left-out' models w/ <chosen 5> ('D3', 'D9', 'D11', 'D17', 'HC6') left-out subjects and record results in experiment results	3rd Aug

MPS 4: Make predictions for <chosen 5> for individual measurements tested and record results (i.e. 5 subjects x 4 measures = 20 rows in table)	4th Aug
MPS 5: Experiment w/ '<chosen 5> (left out)' on (AD) models built from FRC_ files and record results in experiment results (compare w/ single-measure AD subject predictions)	4th Aug
Add optional arg to 'rnn.py' to horizontally concatenate all measurements data together and reduce using 'ft_sel_red' (w/ modifying 'model_pred' to call the same)	4th Aug
Write unique batch files for each model prediction set to launch, including previous and future model prediction sets	4th Aug

Week 2: List of Tasks (5th Aug - 11th Aug)	Date Completed

Add to batch scripts README for model prediction sets and add to script explanations	5th Aug
Sort 'rnn_models' into 'rnn_models_old' as required	5th Aug
MPS 6: Make predictions for '<chosen 5> (left out)' on models w/ subject LO vs models w/ subject not-LO (i.e. '--use_seen')	5th Aug
MPS 7: Make predictions for '<chosen 5> (left out) (act #)' on models built from standard LO subjects and record single-act model predictions in experiment results	5th Aug

Modify 'left-out' arg in 'rnn' to account for specific file name (e.g. 'D2-009' rather than just 'D2') and multiple left-out subjects specified by commas	6th Aug

MPS 8: Experiment w/ '<chosen 5> (left out)' but with the 'D10' outlier subject left out + compare to MPS 3 results in experiment results	7th Aug
MPS 9: Experiment w/ '<chosen 5> (left out)' on models built from single acts (concat) files and record results in experiment results	7th Aug
MPS 10: Experiment w/ '<chosen 5> (left out)' on models built from 'downsampling' and record results in experiment results	7th Aug

MPS 11: Experiment w/ '<chosen 5> (left out)' on models built from measurement-concatenated data and record results in experiment results	8th Aug

Modify 'rnn' and 'model_predictor' to use multiple 'dir's and setup batch file	9th Aug
Report: write full system setup, including running of 'settings.py', required system specs (RAM, GPU), the '.mat' files repositories and modifying 'settings.py'	9th Aug

Report: write data setup and data types section (borrowing heavily from initial report), w/ emphasis on output types	11th Aug

Week 3: List of Tasks (12th Aug - 22nd Aug)	Date Completed

Aims: have last 7 MPS's done, add another 3 sections to report, and review 7 more and 3 previous papers

MPS 13: Experiment w/ '<chosen 5> (left out)' on models built both NSAA and 6minwalk directories	13th Aug
Catch-up call with Bala	13th Aug
Add function to 'graph_creator' to plot true and preds for given row number range and create graphs for MPS 12	13th Aug
MPS 12: Experiment w/ '<chosen 5> (left out)' on models built from single-act files only for output type 'indiv' and single-act 'indiv' predictions in experiment results	13th Aug
Separate the 'dis_3d_pos' functionality from 'comp_stat_vals.py' into its own script, update script README's, append to script explanations, and modify diagrams	13th Aug

MPS 14: Experiment w/ '<chosen 5> (left out)' on models built from measurements that have had features reduced to '20'	14th Aug
Report: add section on documents' significance explanation (e.g. 'nsaa_6mw_info', Google annot sheet, 'RNN Results', 'model_predictions', etc.)	14th Aug
Move Google sheet annotations file to 'documentation' and make all document paths inherit from 'settings.py'	14th Aug

MPS 15: Experiment w/ '<chosen 5> (left out)' on models built from noise-added data (small amount of noise) and record results in experiment results	15th Aug
Report: add glossary of terms (review other sections for terms to add)	15th Aug
Report: add project aims and objectives section (borrowing heavily from initial report)	15th Aug

Add ability for 'rnn.py', when loading 'add_dir=allmatfiles', to only sample a certain amount of data for each of the subjects (e.g. select number of files for subject given by arg)	16th Aug
Add option to 'model_predictor.py' to draw a single sequence from the subject file	16th Aug
Add function to 'model_predictor.py' to combine all final predictions to make a more-accurate prediction for overall NSAA (inc single-act files and D/HC output type)	16th Aug
Report: add to 'experiments and results discussions' a description of how experiment sets and model prediction sets are each carried out (purpose, differences between them, diagrams, etc.)	16th Aug

MPS 16: Experiment w/ '<chosen 5> (left out)' on models built both NSAA and allmatfiles directories (w/ downsampled allmatfiles)	18th Aug
MPS 17: Experiment w/ '<chosen 5> (left out)' but with the assessed file having a single sequence drawn from the total file (e.g. 60 of data evenly sampled over whole assess file)	18th Aug
MPS 18: Experiment w/ '<chosen 5> (left out)' but using the aggregated predictions to compare to non-aggregated predictions	18th Aug
Add option to 'rnn.py' to use entire data set with 'train_test_ratio = 0.0', modify 'model_predictor.py' to account for this, and setup MPS 19	18th Aug
Modify 'model_predictor' to work with subjects never seen before (hence would produce no 'true' output to console or 'model_predictions')	18th Aug

Download new NMB data set, set it up in 'msc_project_files', and modify scripts to use this	19th Aug

Report: write bibliography of all papers used and will use, along with textbooks and webpages used	21st Aug
MPS 19: Experiment w/ '<chosen 5> (left out)' but with entire data set (except LO files) being used as training samples (i.e. train_test_ratio = 0.0)	21st Aug
Report: write section of explaining all directories, including data directories in 'MSc_project_files', the project source dir, the 'rnn_models' and 'RNN_outputs' directories	21st Aug
Report: write section on explaining how to replicate the experiment sets and MPSs, what programs to run w/ what commands, what needs to be set up first, etc	21st Aug

Clone project directory to GitLab	22nd Aug
Report: write RNN review w/ focus on LSTMs and use TensorFlow with RNNs	22nd Aug
Report: write summary of Duchenne, w/ references to previous studies	22nd Aug
Copy local directory to OneDrive (Imperial) and modify 'Directories Overview' to reflect this	22nd Aug

Final Project Tasks (24th Aug - 5th Sep; 13 days)

MPS 20: Repeat MPS 16 but with new NMB data set using all 5 measurements	24th Aug
Modify 'rnn.py' and 'model_predictor.py' to use certain versions of files (e.g. 'V2' or not files)	24th Aug
Write batch script that allows assess of source 'V2' mat file; add to README and script explanations	24th Aug
Write 'file_mover.py' script; add README and add to script explanations and diagram	24th Aug
MPS 21: Experiment w/ 'V2' files left out and assessed on all available 'V2' files	24th Aug

Report: write project timeline and Gantt chart
MPS 22: Experiment w/ 'alt_dirs' with files trained on natural movement and predicting NSAA files (AND vice versa) and record results in experiment results
Write batch script to fully assess from given dir + fn (calling 'ext_raw_measures', 'comp_stat_vals, etc. and doing single-act assessments); add to README, script explanations + diagram
Report: write section on further improvements and project directions to undertake
Report: write outline of 'Final evaluation results' section with final model settings to include: results for left-out subjects, results for altdir test results for NSAA / NMB, results for single-act files
Make table of contents / layout of final report

Report (final): put together the background and initial setup section, including editing and spellcheck each part
Find further 8 papers on HAR using NNs, bookmark, and add to bibliography

Review and add to paper review section: “Deep Convolutional and LSTM...” and “Differential RNNs...”
Review and add to paper review section: “Co-Occurrence Feature Learning...” and “Online Detection and Classification...”
Review and add to paper review section: “Sequential Deep Learning...” and “Long-term Recurrent...”
Review and add to paper review section: “Spatio-Temporal LSTM...” and “A Comprehensive Study...”

Final evaluation set: cross-val over all subjects for sensor magnetic field w/ models using '--no_testset', '--balance_nmb=3', and '--combine_preds'
Report: move final chosen models to directory within project directory, add to 'Final evaluation results' section the directory and the models chosen, and modify 'assess...' batch file and 'model_pred...' to be able to use this new model dir

Add necessary 2 top-level READMEs as required by email