## Sheet1
Stage | Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1: Background Research and Setup | Research + summarise from 7 papers
Presentation of initial background research
Find + make notes from 5 papers on RNNs
Northstar background research and note taking
Type up notes thus far
Find further 5 papers relating to RNNs and action/motion analysis
Create research papers folder and file previous papers
Setup laptop for CUDA / TF GPU
Read and complete programs in 'Python ML', ch 16
Make RNN / CRF presentation (2 slides each, 1 description, 1 usefulness)
Paper review: “Deep, Convolutional, and Recurrent Models for HAR using Wearables”
Do RNN presentation
Type up and make import points from: “Deep, Conv, and Recurrent Models for HAR using Wearables”
Paper review: “Deep Recurrent NN for Mobile HAR with High Throughput”
Paper review: “Hierarchical Recurrent Neural Network for Skeleton Based Action Recognition”
2: Programming of Data Pipeline | Download/setup suit data and create diffs plot function
Add function to extract statistical features of joint files + print results to separate .csv
Create extract/dynamic visualisation functions for all-data files
Setup classes for different file types, comment all code, and commit
Create AD function for accel/magnet/position statistical analysis
Add to DC init function (inc extract table to .csv and read in, and passing to JA objects)
Add Fourier analysis functionality to statistical extraction for AD class (veloc+accel)
Make presentation of 2 weeks inc: suit data format, .py script, next steps
Swap order of col label to be: measure, feature, axis, stat
Create dict mapping from measure name to seg/joint/sens names
Add command line functionality and arguments
Fix crashes-on-close problem with pyplot windows
Add name of file to output col (i.e. one col for if HC or D file)
Add option to 'split up the input JA/AD file w/ 'HC'/'D' labels into numerous files w/ same label
Add function that checks for behaviour abnormality over all features for each file written
Implement 'extract_stat_features' function to be called by write_stats by both classes including all stat functions
Implement function to extract JA .mat files to .csv
Add other stat features (see paper for full list of features to additionally include)
Make display 3D pos plot run in real-time
3: Setup of RNN model and predictor | Implement basic RNN model with .csv output file
(+ continuation of data pipeline modification) | Create README file of 'matfile_analysis'
Edit RNN layout and suppress warnings on output
Add optional argument to automatically delete the created output .csv files at end of command
Eliminate need for 'file name' when 'file type' given as 'dc'
Ensure different file types are written to different subdirectories of 'output_files' (e.g. for AD, JA, DC)
Add alternative to 'split files' in 'matfiles_analysis' that specifies a preferred file length rather than num of splits
Modify 'matfiles_analysis' to work with diff subdirs
Download additional necessary dataset files
Comment both scripts
Add script with various feature reduction techniques
Add option to read in NSS's into df as new column
Implement NSS as labels in RNN script
Adapt RNN to predict north star scores as alternative
Add functionality to extract act scores from .xlxs into df
Stage | Task | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
3: Setup of RNN model and predictor | Annotate D11-D20 NSAA files and edit google sheet
(+ continuation of data pipeline modification) | Fix issue with 'JA/DC all' split_size=1 only showing '19s' on 'y-true'
Add function in RNN to write real and predicted scores to .csv
Create 'mat_act_div' script to divide up .mat files and rewrite to new dir
Fix 3D image pos not ending and exiting issue
Fix 3D image pos distortion issue
Use 'mat_an' to setup 'NSAA\AD', '6minwalk-matfiles\AD', 'direct_csv\DC', and 'direct_csv\JA'
Modify 'ft_red' to work with 'fn=all' argument and encapsulate feature selection/reduction
Modify RNN to work with both stat vals and raw joint angles for both DMD/HC class and NSAA regress
Create .csv file with results of RNN setups (DMD/HC class and NSAA regress for both AD and DC raw joint files)
Change names of all scripts and put them in 'source' directory (alter output dirs and batch as needed)
4: Initial experiments w/ models | Add to 'RNN results' for '6minwalk-matfiles\AD' and 'direct_csv\JA' for both choice='dhc' and 'overall'
(+ continuation of overall system modification) | Modify RNN to predict 17 output nodes for each activity w/ AD files from NSAA
Add optional argument to 'rnn' to write results and settings to relevant columns in 'RNN Results.ods'
Add optional argument to 'comp_stat_vals' to write all files to one 'all' file
Add 'ext_raw_measures' script to extract specific raw measurement values from given AD .mat file(s)
Add R^2 and RMSE as metrics in 'RNN.py' for regression
Implement confusion matrix output in 'RNN.py' for D/HC classification
Experiment for all input options for choice='acts'
Add optional argument to 'RNN.py' to specify proportion of sequence overlap
Add 'all' option for 'measurements' in 'ext_raw_measures.py' and run script with 'measurements=all'
Modify 'RNN.py' to work with raw measurements from local drive
Modify 'add_nsaa_scores' in both scripts to read NSAA scores from 'KineDMD data updates Feb 2019'
Change 'model_dir' to reflect script arguments
Add 'RNN.py' results output to 'write_to_csv'
Add optional 'RNN.py' argument to set num_epochs as argument
Experiment with different raw data measurements from AD files for various RNN outputs
Experiment with various sequence overlap proportion for NSAA\AD stat vals for choice='overall'
Enable 'comp_stat_vals' to extract features from 'single-act' matfiles
Enable 'ext_raw_measures' to work with 'single-act' matfiles and extract all measures from 'single-act' files
Modify 'RNN.py' to work with single-act .mat files to predict single-act NSAA scores
Add a README for 'How to use 3D visualization function'
Comment 'mat_act_div.py' and 'ext_raw_measures.py' scripts
Download missing files from 'NSAA\matfiles\ directory
Create .csv file with all subject info from 3 prev files
Experiment with single-act raw measurements files to predict single-act score (0, 1, or 2)
Move 'output_files' off dropbox into 'msc_project_files' and have all scripts point to there
Write script that loads a trained RNN model and tests on a complete file
Comment 'rnn.py' and 'ft_sel_red.py' scripts
5: Further experimentation w/ models and | Experiment w/ useful raw measurements with longer sequences and larger sequence overlap
writing of suplementary scripts | Modify pipeline to ensure ALL available files are processed
Change both 'add_nsaa_scores' to only use 'nsaa_6mw_matfiles'
Add more experiments with longer seq length and more raw measurements
Download the additional 'NSAA\matfiles'
Write script to create matplotlib graphs from lines in 'RNN Results'
Rerun NSAA stat vales pipeline with new files
Ensure 'model_predictor' works with stat vals output
Modify 'rnn' and 'model_predictor' to use .xlsx file for storing seq_len
Ensure 'graph_creator' withs with all expers and choices, and rerun
Run experiments w/ 'NSAA\AD' diff features and plot graphs
Run experiments w/ 'NSAA\AD' different seq len and overlaps and plot graphs
Modify 'ft_sel_red' to always delete previous 'FT_' files in directory
Make slides of purpose of project, diagram of all scripts, experiments + results thus far, and next steps
Do the video annotations required and fill out the Google sheet
Add option in 'model_predictor' to create ensemble of various raw measurements and stat values
Fix 'rnn.py' to write to 'model_shapes'
Fix 'model_predictor' to work w/ AD files
Add option to 'rnn.py' to create graph of real vs predicted overall NSAA scores
Make 'write_to_csv' write to unique files based on args/epochs and a unique index number
Modify 'ext_raw_measures' to extract 'allmatfiles' files and run
Experiment w/ AD files w/ shorter seq_lens for AD and graph results
Add '--discard_prop' option to 'rnn' to optionally discard every nth element to reduce size of sequence length
Experiment w/ longer seq_lens and discard_prop for jointAngle and graph results
Add option to 'graph_creator.py' to create graph of trues vs preds overall NSAA scores from single file name arg
Modify 'model_predictor.py' to round overall NSAA scores after averaging across models
Write batch script to work with a single 'allmatfiles' or AD file and feed through to 'model_predictor'
Modify 'model_predictor.py' to write and display trues/preds graph
Write batch script to do all package setup and run 'comp_stat_vals', 'ft_sel_red', ext_raw_measures'. 'mat_act_div'
Modify 'file_predictor.cmd' to work with AD source files through pipeline
Add optional 'rnn.py' argument to use additional source dir along with current 'dir' to combine 6minwalk and 6MW
Add optional 'rnn.py' argument to leave a file out
Run 'rnn.py' w/ NSAA top-4 raw measurements and AD for all output types with most ideal seq_len, seq_overlap, etc.
Reorganize batch scripts into subdir of 'source'
Run 'rnn.py' w/ combined 6minwalk and 6MW w/ same data types, output types, etc. as with NSAA
Change RNN_outputs .csv name to be based on sys.argsv
Add optional 'alt_dirs' argument to 'model_predictor' to use different directory(s) to test the file on
Create 'file_predictor_altdirs.cmd' to load an 'allmatfile' file and test it on the NSAA\jointAngle and 6m\jointAngle models
6: Using the model predictor script for model | Modify 'model_predictor.py' to write 'output_strs' to a single test file (each model = 1 row, each string = 1 col of row)
predictions sets and continuation of | Write 'test_altdirs' script that automates the testing of each file in a dir on different dirs
system modifications | Add option to 'graph_creator.py' to graph the results in 'model_predictions.csv'
Experiment w/ all 'allmatfiles' files using 'test_altdirs.py' w/ models trained on both NSAA and 6MW and graph results
Write 'settings' script that stores all global variables used across files ('local_dir', 'source_dir', 'file_types', etc.)
Write 'file_renamer' script to standardize names of 'mat' files in source directories and add to 'setup.cmd'
Write batch script to train RNNs with given file left out then run model predictor on that file
Add option to 'model_predictor.py' to use models that were specifically trained on for given 'fn'
Experiment w/ 'left out' batch script with left-out 'D3' files (i.e. having retrained RNN w/ leaving out 'D3' files each time)
Modify 'comp_stat_vals.py' so files aren't overwritten w/ diff sub-files
Download all '6minwalk-matfiles', '6MW-matFiles', and 'NSAA' files and run 'setup.cmd'
Modify 'model_predictor.py' to work with single-act files
Fix issues w/ 'model_predictions' not being written correctly and rerun 'allmatfiles on NSAA,6minwalk' and 'D3'
Modify 'graph_creator.py' that reads in 'model_predictions' and computes statistical values
7: Documentation of system and experiment | Add script READMEs for 'settings', 'file_renamer', and 'test_altdirs'
results thus far and continuation of | Add script READMEs for 'mat_act_div' and 'ft_sel_red'
system modifications | Add script README for 'ext_raw_measures'
Write 'data_balancer.py' script to balance datasets and have before and after counts of y-labels printed to output
Modify 'model_predictor' to ensure that non-balanced and non-left out models are used when appropriate
Refactor 'graph_creator with everything in functions and more appropriate arguments
Add function to 'graph_creator' to, for a given file and plot results of single-act predictions
Experiment w/ single-act 'D11' files tested on 'D11-left-out' models to approximate overall NSAA score
Add script README for 'graph_creator'
Experiment w/ up and down balanced datasets for left-out 'D3' file on models for all outputs and record the results
Experiment w/ left-out 'D11' natural movement files to train the 3 models
Stage | Task | 17 | 18 | 19 | 20 | 21 | 22 | 23
7: Documentation of system and experiment | Add general README to GitHub repo outlining the project and how the repo is laid out
results thus far and continuation of | Add script README for 'data_balancer'
system modifications | Update powerpoint diagram and add to script ecosystem overview and GitHub 'source' 'README.md'
Write results discussion of experiment sets 1 - 2
Write results discussion of experiment sets 3 - 4
Add script README for 'rnn'
Download additional data files, modify pipeline for new 'left-out' dir, and use it on each of these
Add script README for 'model_predictor'
Add script README covering all batch files
Write script discussion w/ copy-paste of script READMEs and include updated powerpoint diagram
Write results discussion of experiment sets 5 – 8
Add table of details for experiments 1 – 8
Write results discussion for experiments 82 - 98
Write results discussion of 'model_predictions' for 'altdirs'
Write results discussion of 'model_predictions' for 'left-out' models
8: Experimentation with model predictions | Download new Google sheet and modify 'mat_act_div.py' to use this instead of previous one and run
sets for MPS 3 - 11 and continuous | Add optional arg to 'mat_act_div.py' to create source files with single acts but concatenated together
system modifications to enable MPS's | Add optional arg to 'ft_sel_red' to reduce dimensions on whole dataset, rather than on file by file basis and run
Modify and run 'comp_stat_vals' and 'ext_raw_measures' on single_act concat and non-concat files
Modify 'rnn.py' and 'model_predictor.py' to use 'single_acts_concat' files and differently feature-reduced dataset
Write 'predictions_selector' script that reads 'model_predictions.csv' with given arguments
Add 'cnn_preprocessing' function to 'rnn.py'
Build CNN models on 'D3', 'D9', 'D11', 'D17', 'HC6' left-out subjects, and provide 'rnn_outputs' results
Modify reference table w/ correct 'D2'/'D3' entries and re-run all setup lines that make use of this file
Add README script for 'predictions_selector', add it to script explanations, and modify pipeline diagrams
Add optional args to 'rnn.py' to standardize all features of data and add Gaussian noise to the dataset
Restructure 'plans_and_presentations' and 'project_files' dirs into outer dir
Report: write summary of use of Python, IDE, and TensorFlow
Build standard 'left-out' models w/ <chosen 5> ('D3', 'D9', 'D11', 'D17', 'HC6') left-out subjects
MPS 4: Make predictions for <chosen 5> for individual measurements tested and record results
MPS 5: Experiment w/ '<chosen 5> (left out)' on (AD) models built from FRC_ files
Add optional arg to 'rnn.py' to horizontally concatenate all measurements data together
Write unique batch files for each model prediction set to launch, including previous and future MPS's
Add to batch scripts README for model prediction sets and add to script explanations
Sort 'rnn_models' into 'rnn_models_old' as required
MPS 6: Make predictions for '<chosen 5> (left out)' on models w/ subject LO vs models w/ subject not-LO
MPS 7: Make predictions for '<chosen 5> (left out) (act #)' on models built from standard LO subjects
Modify 'left-out' arg in 'rnn' to account for specific file name (e.g. 'D2-009' rather than just 'D2')
MPS 8: Experiment w/ '<chosen 5> (left out)' but with the 'D10' outlier subject left out
MPS 9: Experiment w/ '<chosen 5> (left out)' on models built from single acts (concat) files
MPS 10: Experiment w/ '<chosen 5> (left out)' on models built from 'downsampling'
MPS 11: Experiment w/ '<chosen 5> (left out)' on models built from measurement-concatenated data
Modify 'rnn' and 'model_predictor' to use multiple 'dir's and setup batch file
9: Creation of final report and finishing the | Report: write full system setup, including running of 'settings.py' and required system specs (RAM, GPU)
execution of MPS's 12 - 22, and making of | Report: write data setup and data types section (borrowing heavily from initial report), w/ emphasis on output types
necessary system modifications | MPS 13: Experiment w/ '<chosen 5> (left out)' on models built both NSAA and 6minwalk directories
Add function to 'graph_creator' to plot true and preds for given row number range and create graphs for MPS 12
MPS 12: Experiment w/ '<chosen 5> (left out)' on models built from single-act files only
Separate the 'dis_3d_pos' functionality from 'comp_stat_vals.py' into its own script, update script README's
MPS 14: Experiment w/ '<chosen 5> (left out)' on models built from measurements that have had features reduced to '20'
Report: add section on documents' significance explanation
Move Google sheet annotations file to 'documentation' and make all document paths inherit from 'settings.py'
MPS 15: Experiment w/ '<chosen 5> (left out)' on models built from noise-added data (small amount of noise) and record results
Report: add glossary of terms (review other sections for terms to add)
Report: add project aims and objectives section (borrowing heavily from initial report)
Add ability for 'rnn.py', when loading 'add_dir=allmatfiles', to only sample a certain amount of data for each of the subjects
Add option to 'model_predictor.py' to draw a single sequence from the subject file
Add function to 'model_predictor.py' to combine all final predictions to make a more-accurate prediction for overall NSAA
Report: add to 'experiments and results discussions' a description of how experiment sets and MPS's are run
MPS 16: Experiment w/ '<chosen 5> (left out)' on models built both NSAA and allmatfiles directories (w/ downsampled allmatfiles)
MPS 17: Experiment w/ '<chosen 5> (left out)' but with the assessed file having a single sequence drawn from the total file
MPS 18: Experiment w/ '<chosen 5> (left out)' but using the aggregated predictions to compare to non-aggregated predictions
Add option to 'rnn.py' to use entire data set with 'train_test_ratio = 0.0' and modify 'model_predictor.py'
Modify 'model_predictor' to work with subjects never seen before
Download new NMB data set, set it up in 'msc_project_files', and modify scripts to use this
Report: write bibliography of all papers used and will use, along with textbooks and webpages used
MPS 19: Experiment w/ '<chosen 5> (left out)' but with entire data set (except LO files)
Report: write section of explaining all directories, including data directories in 'MSc_project_files'
Report: write section on explaining how to replicate the experiment sets and MPSs, etc.
Clone project directory to GitLab
Report: write RNN review w/ focus on LSTMs and use TensorFlow with RNNs
Report: write summary of Duchenne, w/ references to previous studies
Copy local directory to OneDrive (Imperial) and modify 'Directories Overview' to reflect this
MPS 20: Repeat MPS 16 but with new NMB data set using all 5 measurements
Modify 'rnn.py' and 'model_predictor.py' to use certain versions of files (e.g. 'V2' or not files)
Write batch script that allows assess of source 'V2' mat file; add to README and script explanations
Write 'file_mover.py' script; add README and add to script explanations and diagram
MPS 21: Experiment w/ 'V2' files left out and assessed on all available 'V2' files